DOCUMENT: PROJECT PLANNING

| Phase | Project Planning Phase |
| --- | --- |
| Document | Project Planning (Product Backlog, Sprint Planning, Stories, Story Points) |
| Project Name | PetPaws – Pet Foods & Accessories Store |
| Team ID | [TEAM-ID] |
| Date | 14 June 2026 |
| Maximum Marks | 5 Marks |

# Product Backlog, Sprint Schedule & Estimation

Total Story Points: 76 | Sprints: 4 | Sprint Duration: 6 days each | Team Velocity: ~20 story points per sprint (average)

| Sprint | Epic | USN | User Story / Task | Story Pts | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| S-1 | Auth & User | USN-1 | User registration with JWT | 3 | High | [Member 1] |
| S-1 | Auth & User | USN-2 | User login + admin login | 2 | High | [Member 1] |
| S-1 | Product Catalog | USN-3 | Product listing with category + pet-type filters | 5 | High | [Member 2] |
| S-1 | Product Catalog | USN-4 | Keyword search + sort + pagination | 3 | High | [Member 2] |
| S-1 | Product Catalog | USN-5 | Product detail page: gallery, variants, reviews tab | 3 | High | [Member 3] |
| S-1 | Cart | USN-6 | Add/update/remove cart items; real-time badge | 4 | High | [Member 3] |
| S-1 | Admin Products | USN-15 | Admin product CRUD + soft-delete | 5 | High | [Member 4] |
| S-2 | Wishlist | USN-7 | Wishlist add/remove/move-to-cart | 3 | Medium | [Member 1] |
| S-2 | Checkout | USN-8 | 3-step checkout wizard (Address → Payment → Review) | 8 | High | [Member 2,3] |
| S-2 | Checkout | USN-9 | Saved addresses selector at checkout | 2 | High | [Member 2] |
| S-2 | Orders (User) | USN-10 | Order history page with status filter tabs | 3 | High | [Member 4] |
| S-2 | Orders (User) | USN-11 | Order detail with timeline + cancel + tracking | 4 | High | [Member 4] |
| S-3 | Reviews | USN-12 | Review submission + verified purchase badge + rating aggregation | 5 | Medium | [Member 1,2] |
| S-3 | Profile | USN-13 | Profile update, password change, address CRUD | 4 | Medium | [Member 3] |
| S-3 | Admin Dashboard | USN-14 | KPI cards, revenue chart, low-stock, top products | 6 | High | [Member 4] |
| S-3 | Admin Orders | USN-16 | Admin order table, status update, tracking number | 4 | High | [Member 4] |
| S-4 | Admin Customers | USN-17 | Customer search + activate/deactivate | 3 | Medium | [Member 1] |
| S-4 | Store Settings | USN-18 | Shipping, tax, banners, category config | 4 | Medium | [Member 2] |
| S-4 | QA & Deploy | — | Database seeding, end-to-end testing, deployment to Vercel + Railway | 5 | High | [All] |

# Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Pts | Duration | Sprint Start | Sprint End (Planned) | Story Pts Completed | Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 25 | 6 Days | 31 Jan 2025 | 05 Feb 2025 | 25 | 05 Feb 2025 |
| Sprint-2 | 20 | 6 Days | 07 Feb 2025 | 12 Feb 2025 | 20 | 12 Feb 2025 |
| Sprint-3 | 19 | 6 Days | 14 Feb 2025 | 19 Feb 2025 |  |  |
| Sprint-4 | 12 | 6 Days | 21 Feb 2025 | 26 Feb 2025 |  |  |

## Velocity

Team velocity = 20 story points per 6-day sprint (average across Sprint 1 and Sprint 2). Average Velocity (AV) per day = 20 ÷ 6 ≈ 3.3 story points per day. This metric is used to forecast sprint capacity and adjust scope for Sprint 3 and Sprint 4.

## Burndown Chart Description

A burndown chart tracks remaining story points against elapsed sprint days. For a 6-day sprint with 20 story points:

- Day 0 (Start): 20 story points remaining

- Day 1: ~17 points remaining

- Day 2: ~13 points remaining

- Day 3: ~10 points remaining (midpoint)

- Day 4: ~7 points remaining

- Day 5: ~3 points remaining

- Day 6 (End): 0 points remaining — sprint complete

The ideal burndown line is a straight diagonal from 20 (Day 0) to 0 (Day 6). Deviations above the ideal line indicate sprint risk. Deviations below indicate the team is ahead of schedule.